## Project schedule
| Data Governance | [6 empty] | Project start: | [7 empty] | 2025-10-27
| City of Wichita | Project lead | [5 empty] | Display week: | [7 empty] | 1
[8 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15
| TASK | ASSIGNED TO | DELIVERABLE (create a Team Folder and upload your Deliverable for each task and attach the link in appropriate cells below for team reference) | PROGRESS | START | END | time axis 2025-10-27 to 2025-12-21
 | time axis 2025-10-27 to 2025-12-21
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| Data Governance and System Requirements Review |  | Link to Deliverable Folder
| 1. Conduct a comprehensive review of the CoW’s Data Governance framework to ensure alignment with industry standards |  |  | 0%
| 1.1 Collect and begin reviewing all existing data governance documentation from the CoW |  | Initial Summary |  | 2025-10-13 | 2025-10-19
| 1.2 Identify the key industry standards and regulations relevant to the CoW's operations |  | Summary of industry standard |  | 2025-10-13 | 2025-10-19
| 1.3 Draft Initial findings on the governance framework |  | Draft version |  | 2025-10-19 | 2025-10-24
| 1.4 Draft the Data Governance review report. |  | Draft version |  | 2025-10-24 | 2025-10-30
| 2. Analyze system requirements for a revamped data storage and analysis environment in collaboration with CoW’s IT department |  |  | 0%
| 2.1 Collect all existing technical documentation (e.g., architecture diagrams, system inventories) |  | Initial Summary |  | 2025-10-13 | 2025-10-19 | 7
| 2.2 Identify current storage systems how data is stored, ingested, and managed (e.g., databases, data lakes, cloud infrastructure, ETL pipelines) |  | Data Storage Requirement |  | 2025-10-19 | 2025-10-24 | 6
| 2.3 Identify current data anlysis & security how data is used and secured (e.g., analytics tools, BI dashboards, access controls, encryption, logging) |  | Data User Access & Security Control Requirement |  | 2025-10-24 | 2025-10-29
| 2.4 Consolidate findings to present diagram of the current system architecture and its main pain points |  |  |  | 2025-10-29 | 2025-10-24
| 2.5 Draft the detailed system requirements document |  | Map governance rules to technical requirements
| 3. Finalization and Delivery |  |  | 0%
3.1 Check the governance report for technical feasibility, and the system requirements for compliance
3.2 Incorporate feedback from the peer review and finalize the documents
| 3.3 Prepare a joint presentation summarizing the findings and recommendations from both deliverables for the CoW |  |  |  | 2025-11-01 | 2025-11-03
Development of Data Storage and Analysis Environment
|  |  |  | 50% | 1899-12-31 | 1900-01-04 | 5
|  |  |  | 50% | 1900-01-02 | 1900-01-07 | 6
[5 empty] | 1900-01-07 | 1900-01-10 | 4
[5 empty] | 1900-01-07 | 1900-01-09 | 3
[5 empty] | 1900-01-07 | 1900-01-10 | 4
Public Survey Data Analysis
|  |  |  | 50% | 1900-01-14 | 1900-01-19 | 6
|  |  |  | 60% | 1900-01-20 | 1900-01-24 | 5
|  |  |  | 50% | 1900-01-25 | 1900-01-30 | 6
|  |  |  | 25% | 1900-01-31 | 1900-02-04 | 5
|  |  |  | 25% | 1900-01-25 | 1900-01-29 | 5
Power BI Dashboard Development
|  |  |  | 25% | 1900-01-16 | 1900-01-19 | 4
|  |  |  | 25% | 1900-01-19 | 1900-01-23 | 5
|  |  |  | 50% | 1900-01-24 | 1900-01-27 | 4
|  |  |  | 60% | 1900-01-21 | 1900-01-24 | 4
|  |  |  | 50% | 1900-01-23 | 1900-01-28 | 6
Power BI Dashboard Development
|  |  |  | 25% | 1900-01-18 | 1900-01-21 | 4
|  |  |  | 25% | 1900-01-21 | 1900-01-25 | 5
|  |  |  | 50% | 1900-01-26 | 1900-01-29 | 4
|  |  |  | 60% | 1900-01-23 | 1900-01-26 | 4
|  |  |  | 50% | 1900-01-25 | 1900-01-30 | 6
Insert new rows ABOVE this one
Formulas:
Display week: = [Display week:, row below]